## Under production Orders (hidden)
No. | Done by | # | PO# | Proj. No | SO number | Customer | JOH | QTY | Sector | Statues | Dubai/JED/PURSHES | Delivery based on the contract | ETA Dubai ¦ KSA | ETA Purchase | Dubai Remarks | JED Remarks | AFSD / Purchase Remarks | NO of Delevried | Pending Purchase Items | 2024 | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | 2026 | Plentily conditions | Plentily ( Safe / Applied / Critical ) | Plentily Amount (SAR) | Total Value + VAT | Summary Status
1 | Nader | NEW | 5929 | 1921 | 103009 | Afras - Custom project | Combined Fire & Rescue Vehicle | 9 | Private | In Progress | Dubai | 3 Units,12-Dec-2025 3 Units, 12-Feb-2026 3 Units, 13-Apr-2026 | 25-Sep-2025 25-Oct-2025 25-Dec-2025 |  | 2 units will be ready for FAT 25 Sep 2025 3 units will be ready for FAT 25 Oct 2025 4 units will be ready for FAT 10 Dec 2025 | [5 empty] | SEP: 2; OCT: 3; DEC: 4 |  | 0.5% deduction for each late week, up to a maximum of 10%. | SAFE | 0 | 21155400 | In Progress ¦ No Missing ¦ SAFE
2 |  |  |  | 1923 |  |  | Light Rescue Vehicle | 9 | Private | In Progress | Dubai | 3 Units,12-Dec-2025 3 Units, 12-Feb-2026 3 Units, 13-Apr-2026 | 25-Sep-2025 25-Oct-2025 25-Dec-2025 |  | 2 units will be ready for FAT by 25 Sep 2025 3 units will be ready for FAT by 25 Oct 2025 4 units will be ready for FAT by 10 Dec 2025 | [5 empty] | SEP: 2; OCT: 3; DEC: 4 |  | 0.5% deduction for each late week, up to a maximum of 10%. | SAFE | 0 | 16353000 | In Progress ¦ No Missing ¦ SAFE
3 |  |  |  | 1924 |  |  | Water Tanker | 20 | Private | In Progress | Dubai | 5 Units,12-Dec-2025 5 Units, 12-Feb-2026 10Units, 13-Apr-2026 | 25-Sep-2025 25-Oct-2025 25-Dec-2025 |  | 5 units will be ready for FAT by 25 Sep 2025 5 units will be ready for FAT by 25 Oct 2025 10 units will be ready for FAT by 10 Dec 2025 | [5 empty] | SEP: 5; OCT: 5; DEC: 10 |  | 0.5% deduction for each late week, up to a maximum of 10%. | SAFE | 0 | 37381900 | In Progress ¦ No Missing ¦ SAFE
4 |  |  |  | 1922 |  |  | Rapid Intervention Vehicle | 9 | Private | In Progress | Dubai | 3 Units,12-Dec-2025 3 Units, 12-Feb-2026 3 Units, 13-Apr-2026 | 25-Sep-2025 25-Oct-2025 25-Dec-2025 |  | 2 units will be ready for FAT by 25 Sep 2025 3 units will be ready for FAT by 25 Oct 2025 4 units will be ready for FAT by 10 Dec 2025 | [5 empty] | SEP: 2; OCT: 3; DEC: 4 |  | 0.5% deduction for each late week, up to a maximum of 10%. | SAFE | 0 | 9108000 | In Progress ¦ No Missing ¦ SAFE
5 |  |  |  | 1920 |  |  | Hazmat Vehicle | 7 Aug | Private | In Progress | Dubai | 2 Units,12-Dec-2025 3 Units, 12-Feb-2026 2 Units, 13-Apr-2026 | 25-Sep-2025 25-Oct-2025 |  | Chassis will be received Mid of AUG 3 units will be ready for FAT by 25 Sep 2025 4 units will be ready for FAT by 30 Oct 2025 | [5 empty] | SEP: 3; OCT: 4 |  | 0.5% deduction for each late week, up to a maximum of 10%. | SAFE | 0 | 24101700 | In Progress ¦ No Missing ¦ SAFE
6 |  |  | Al Jeel PO#6555 |  | 103178 | SRCA | Electrical Str. | 120 | Gov. | Completed | Purchase | 2025-06-05 | Delivered | [7 empty] | JUN: 120 Item |  | 1% deduction for each late week, up to a maximum of 6% | SAFE | 0 | 19441750 | Completed ¦ No Missing ¦ SAFE
7 |  | 2024 | 5818 | 1906 | 102964 | SRCA - Ambulances | Nupco - 57 ambulances | 57 | Gov. | Pending | JED | 2026-06-17 | Irfan Nothing invoiced waiting update | 2025-10-10 | 48 kits have been delivered. 3 units have been delivered. 6 units are nearly ready, and we will arrange shipping soon. materials are still pending for all delivered units. | All chassis received. - Awaiting pending materials and kits from Dubai. - 15 kits received in 3 containers on 29.03.2025. - Pending list for 15 sets sent to Josvin on 09.04.2025. - 33 kits received (2nd lot) on 29.04.2025; pending list sent to Dubai. - Awaiting balance materials from Dubai. - Partial items received in 2 containers on 25.06.2025. - Partial items received in 1 container on 26.06.2025. - Remaining items ETA: 15.07.2025 (still not received). |  |  | Qty: 57 1.Medsource Extrication Device 2.Aluminium Scoop Stretcher (MS-SCP123-S) 3.Head Immobilizer (MS-91000) 4.Cervical Collar Adult (MS-92500) 5.Pediatric Immobilization Board (MS-PIB-1) 6.Spider Straps (MS-ST11PTR) 7.Traction Splint Kit (MS-TLS-3) 8.Flex-All Splint (MS-SPLINT) 9.Deluxe Spine Board (MS-93000) 10.Power Load System (6390) - Stryker 11.Accuvac Pro Suction (WM11645) 12.Stryker POWER-PRO XT Cot (6506) 13.LP 15 Monitor Defibrillator (99577-001411) 14.Chest Compression Machine (Lucas 3) 15.Stair Chair (ST10453 - Spencer) 16.Spencer 4BELL Chair (ST10501) 17.Portable Ventilator (T1 - HAMILTON) 18.Chest Compressor (Autopulse - Zoll) 19.Hand Sanitizer w/ Dispenser Qty: 114 20.Oxygen Regulator (15002-03 - Allied) Qty: 228 21.Oxygen Mask with Adult |  | JUN: 3; AUG: 48 |  | 1% deduction for each late week, up to a maximum of 6% | SAFE | 0 | 69245310 | Pending ¦ Missing Material ¦ SAFE
8 |  |  | 4083 | 1593 | 10699 | SAR | FIRE FIGHTING & RESCUE VEHICLE | 15 | Gov. | In Progress | Dubai | 2024-09-19 | 2025-11-01 | 2025-09-10 | Units will be ready by Nov 2025 |  |  |  |  | 2024-09-19 | NOV: 15 |  | 0.25% deduction for each late week, up to a maximum of 6% | APPLIED | 3399105.6 | 44496375 | In Progress ¦ No Missing ¦ APPLIED
9 |  |  |  | 1589 |  |  | RailRoad Type I ambulance | 6 | Gov. | In Progress | [8 empty] | Qty: 7 1. Oxygen Cylinder Steel Qty: 6 2. Mounting Bracket for LIFEPAK 15 3. Stair Chair Stair‑Pro 4. Double Fold Pole Stretcher Qty: 1 5. Professional Trauma Bag Qty: 9 6. Restraint Model 430 |  | NOV: 6 |  |  | APPLIED |  | 12155385 | In Progress ¦ Missing Material ¦ APPLIED
10 | [6 empty] | NFPA 1917 | 1 | Gov. | [27 empty] | 145475 | ¦ No Missing ¦ | bar: NOV
11 | [6 empty] | AMC-3 years ambulances | 1 | Gov. | [27 empty] | 1242000 | ¦ No Missing ¦ | bar: NOV
12 | [6 empty] | AMC-3 years firetrucks | 1 | Gov. | [27 empty] | 4830000 | ¦ No Missing ¦ | bar: NOV
13 |  |  | 5001 | 1801 | 102741 | SICLI - TAX PROJECT | COMBINED VEHICLES - Mercedes | 2 | Private | Pending | Dubai | 2025-04-03 | ASD |  |  | 2 units receved in KSA from DXB | in Jed pending accessories | 2 |  | 2025-04-03 | AUG: 2 |  | 1% deduction for each late week, up to a maximum of 6% | SAFE | 259440 | 4324000 | Pending ¦ No Missing ¦ SAFE
14 | [6 empty] | WATER TANKERS - IVECO | 4 | Private | Completed |  | 2024-11-03 | 2025-05-01 |  |  | 4 units already delivered |  | 4 |  | 2024-11-03 | MAY: 4 |  | 1% deduction for each late week, up to a maximum of 6% | SAFE | 402960 | 6716000 | Completed ¦ No Missing ¦ SAFE
15 |  |  |  | 1799 |  |  | LIGHT RESCUE VEHICLES - FORD F550 | 2 | Private | Pending |  | 2025-04-03 | ASD |  |  | 2 units receved in KSA from DXB | in Jed pending accessories | 2 |  | 2025-04-03 | AUG: 2 |  | 1% deduction for each late week, up to a maximum of 6% | SAFE | 206310 | 3438500 | Pending ¦ No Missing ¦ SAFE
16 | Zohairy | NEW | 5944 | SASO issue | 103013 | Sicli - RIV | RIV | 1 | Private | Completed | Dubai | SASO Issue Solved | ASD | [20 empty] | 1% deduction for each late week, up to a maximum of 6% | SAFE | 0 | 563500 | Completed ¦ No Missing ¦ SAFE
17 |  |  | 6151 |  | 103084 | Royal air defense | water tanker (18,000 Ltrs) | 2 | Gov. | In Progress | Dubai | 2026-01-28 | 2026-01-28 | [20 empty] | up to a maximum of 6% | SAFE | 0 | 3205050 | In Progress ¦ No Missing ¦ SAFE
18 | [6 empty] | RIV F-550 | 3 | Gov. | In Progress | Dubai | 2026-01-28 | 2026-01-28 | [21 empty] | SAFE |  | 5476185 | In Progress ¦ No Missing ¦ SAFE
19 |  |  | 6772 | 103165 | 103165 | Royal air defense | Type II Ambulance | 1 | Gov. | Pending | JED | 2025-08-20 | 2025-10-15 | 2025-10-15 |  | Need to know the Project number and required the Specification . |  |  | Qty: 1 MX‑PRO R3‑6082 stretcher – STRYKER | Qty: 1 MX‑PRO R3‑6082 stretcher – STRYKER | AUG: 1; OCT: 1 Unit |  | up to a maximum of 6% | APPLIED | 43677 | 727950 | Pending ¦ Missing Material ¦ APPLIED
20 |  | 2024 | 3605 |  | 102079 | Dr. Sulaiman Al Habib Hospital | Type I ambulance on Ford | 1 | Private | Completed | Dubai | Delivered, May 2025 | Delivered, May 2025 |  | Delivered | [19 empty] | SAFE |  | 831000 | Completed ¦ No Missing ¦ SAFE | bar: JAN to DEC
21 |  |  | 4109 | 1605/1606 | 102412 | KFSHRC - RIYADH | Hazmat & Hazard | 2 | Semi-Gov. | In Progress | Dubai | 2024-09-03 | 2025-07-14 |  | units will be shipped by 11 or 14 July 2025 |  |  |  |  | 2024-09-03 | JUL: 2 |  | up to a maximum of 6% | APPLIED | 127905.3 | 2131755 | In Progress ¦ No Missing ¦ APPLIED
22 |  |  | 5297 |  | 102826 | Zahrat Al Amaal | Ambulance Type II(2) | 2 | Private | Pending | Dubai/JED | The vehicle in factory, waiting for the client’s payment. 28/1/2025 | 10-SEP-2025 based on al Jeel ETA | 2025-09-10 | Delivered to JED |  | waiting 2 strechers from Al Jeel PO# 5561 |  | Qty: 2 Each 1. Aluminum Oxygen Cylinder 2. Stryker MX‑PRO R3 X‑Frame Ambulance Cot |  | SEP: 2 |  | up to a maximum of 6% | APPLIED | 55200 | 920000 | Pending ¦ Missing Material ¦ APPLIED | NO Palinty
23 |  |  | 5186 | 1822 | 102800 | SICLI - TAX PROJECT | HAZAMT VEHICLE | 2 | Private | In Progress | Dubai | 2025-05-22 | FAT 10 Aug 2025 |  | unit will be ready for FAT by 10 Aug 2025 | [5 empty] | AUG: 2 |  | 1% deduction for each late week, up to a maximum of 6% | APPLIED | 369978 | 6166300 | In Progress ¦ No Missing ¦ APPLIED
24 |  |  |  | 1821 |  |  | RIV(2) | 2 | Private | In Progress | Dubai | 2025-01-22 | Waiting the PO to be sent to Dubai |  |  |  | waiting the factory check from the clinet |  |  |  | AUG: 2 |  | 1% deduction for each late week, up to a maximum of 6% | APPLIED | 73830 | 1230500 | In Progress ¦ No Missing ¦ APPLIED
25 | Abdullah | NEW | PO #1970 6342 / WO # 25616597 | 1847 | 103074 | MOD / prince Sattam University - Nupco Alkharj | Type II ambulances | 15 | Gov. | In Progress | JED | 2025-11-20 | Qadomi: Nov - 2025 | 2025-10-10 |  | 9 chassis Received. Partial Drawings received on 08/07/2025. remaining drawings required. Awaiting Kits from Dubai - |  |  | Qty: 15 Each 1.Medsource Extrication Device 2. Aluminium Scoop Stretcher 3. Head Immobilizer Complete Set 4. Adjustable Cervical Collar 5. Pediatric Immobilation Board 6. Spider Straps with Reflective Tape 7. Adult Traction Splint Kit 8. Flex‑All Splint 9. Deluxe Spine Board 10. LP 15 Monitor Defibrillator 11. Child Traction Splint Kit 12. 4‑Bell Stair + MAX 10G Fastening System 13. Spencer 4‑Bell Foldable Transfer Chair 14. Autopulse Chest Compressor |  | NOV: 15 |  | 1% deduction for each late week, up to a maximum of 6% | CRITICAL | 0 | 11584300 | In Progress ¦ Missing Material ¦ CRITICAL
26 |  |  | 6162 | 1952 | 103088 | SRCA | Electrical ambulance | 10 | Gov. | In Progress | Dubai | 2025-12-27 | Januray 2026 |  | Units delivery is on Januray 2026 |  | factory postpone to jan 2026 | [15 empty] | 10 | 1% deduction for each late week, up to a maximum of 6% | CRITICAL | 0 | 6000000 | In Progress ¦ No Missing ¦ CRITICAL
27 |  |  | 6775 | 1730 | 103076 | Amal hospital - Tabouk | Medical Item | 1 | Gov. | Pending | Dubai | 2025-06-05 | Sttar |  |  |  | PO to Dubai as instruction | [16 empty] | 1% deduction for each late week, up to a maximum of 6% | APPLIED | 2305.5 | 38425 | Pending ¦ No Missing ¦ APPLIED
28 |  | 2024 | 4906 | 1791 |  | King Faisal Specialist Hospital | Type I Ambulance | 1 | Semi-Gov. | In Progress | Dubai | 2025-04-30 | 2025-10-18 |  | Unit will be ready for delivery on Oct 2025 | [18 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 39174 | 652900 | In Progress ¦ No Missing ¦ APPLIED | bar: JAN to DEC
29 |  |  | 5120 | 1817 | 102768 | MEENA HEALTH | DENTAL CLINIC | 1 | Private | Pending | Dubai | 2024-11-04 | Waiting for the X-ray machine |  | Delivered |  | Waiting for the X-ray machine |  |  | 2024-11-04 | [13 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 46500 | 775000 | Pending ¦ No Missing ¦ APPLIED | NO Palinty | bar: JAN to DEC
30 |  |  | 4868 | 1772 | 102703/204083 | Saudi Royal Air Dfense | Type II Ambulance | 1 | Gov. | Completed | Dubai | 2024-03-30 | Delivered May - 25 | [5 empty] | Qty: 2 1. Oxygen Cylinder Steel CGA 540, 3000L Qty: 1 2. Head Immobilizer Complete Set | 2024-03-30 | [13 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 33300 | 555000 | Completed ¦ Missing Material ¦ APPLIED | bar: JAN to DEC
31 |  |  | Al Jeel PO#5835 |  | 102960 | Nupco - Al Qassem - مستشفى الملك عبدالله | Supply of Medical Items | 1 | Gov. | Pending | Purchase | 2024-11-12 | 2025-10-10 | 2025-10-10 |  |  | Not received from supplier (pending LC 18M) Not received from supplier waiting ETA |  | Qty: 3 Each 1. Power Load System 2. Stryker POWER-PRO XT Cot 3. LIFEPAK 1000 Defibrillator | 2024-11-12 | OCT: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 513250 | Pending ¦ Missing Material ¦ APPLIED
32 |  |  | LOCAL |  | 102935 | Nupco - Al Jubail - الهيئة الملكية | Supply of Medical Items | 2 | Gov. | Completed | Purchase | 2025-10-08 | 2025-07-05 |  |  |  | Done we receive |  |  |  | JUL: 1 Item |  | 1% deduction for each late week, up to a maximum of 6%. | SAFE | 0 | 156000 | Completed ¦ No Missing ¦ SAFE
33 |  |  | LOCAL |  | 102957 | Nupco - Makkah- مستشفى قوى الامن | Supply of Medical Items | 1 | Gov. | Completed | Purchase | 2024-11-08 | ASD |  |  |  | Done we receive |  |  |  | JUL: 2 Item |  | 1% deduction for each late week, up to a maximum of 6%. | SAFE | 0 | 91050 | Completed ¦ No Missing ¦ SAFE
34 |  |  | Al Jeel PO#5727 |  | 102934 | Nupco - Riyadh - مدينة الملك عبدالعزيز | Supply of Medical Items | 1 | Gov. | Pending | Purchase | 2025-08-22 | 2025-09-10 | 2025-09-10 |  |  | Not received from supplier (From LC 2.5 M |  | Qty: 3 1. LIFEPAK 1000 Defibrillator |  | SEP: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 25500 | Pending ¦ Missing Material ¦ APPLIED
35 |  |  | Al Jeel PO#5725 |  | 102933 | Nupco - maddinah - مستشفى الامير محمد | Supply of Medical Items | 1 | Gov. | Completed | Purchase | 2025-02-23 | 2025-09-10 | 2025-09-10 |  |  | Not received from supplier (From LC 2.5 M LIFEPAK 1000 Defibrillator, Standard Accessories and Defib Pads for Adult/Paediatric/Infant 7,500.00 ر.س.‏ 3 remaining material |  | Qty: 2 1. LIFEPAK 1000 Defibrillator | [14 empty] | 1% deduction for each late week, up to a maximum of 6%. | SAFE | 0 | 17000 | Completed ¦ Missing Material ¦ SAFE
36 |  |  | Al Jeel PO#5835 |  | 102958 | Nupco - Jizan - Jizan University | Supply of Medical Items | 1 | Gov. | Pending | Purchase | 2025-05-01 | 2025-10-10 | 2025-10-10 |  |  | Not received from supplier (From LC 2.5 M LIFEPAK 1000 Defibrillator, Standard Accessories and Defib Pads for Adult/Paediatric/Infant 7,500.00 ر.س.‏ 2 remaining material |  | Qty: 1 1. Power Load System |  | OCT: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 163750 | Pending ¦ Missing Material ¦ APPLIED
37 |  |  | LOCAL |  | 102957 | Nupco - Jizan - Jizan University | Supply of Medical Items | 1 | Gov. | Completed | Purchase | 2025-02-07 | 2025-07-05 |  |  |  | Done we receive |  |  |  | JUL: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 92800 | Completed ¦ No Missing ¦ APPLIED
38 | Ayman | NEW | Al Jeel PO#5835 |  | 103077 | KAH - AlHasa | Medical Item | 1 | Gov. | Pending | Purchase | 2025-04-27 | 2025-10-01 |  |  |  | Not received from supplier (pending LC 18M) Not received from supplier waiting ETA |  | Qty: 4 1. Power Load System 2. Stryker POWER-PRO XT Cot |  | OCT: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 650500 | Pending ¦ Missing Material ¦ APPLIED
39 |  |  | Al Jeel PO#6315 |  | 103111 | SRCA | Medical Item | 1 | Gov. | Pending | Purchase | 2025-07-14 | 2025-12-01 |  |  |  | Yousef Ali, 6/18 :Received Performa invoice from supplier to start LC. |  | Qty: 50 1- Accuvac Pro Portable Suction Qty: 200 2- Head Immobilizer Complete Set Qty:25 3- Stryker MX-PRO R3 X-Frame Amb Cot |  | DEC: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 963500 | Pending ¦ Missing Material ¦ APPLIED
40 |  | 2024 | 4951 | 1792 | 102729 | Navy | Type II ambulances | 11 | Gov. | In Progress | Dubai | 2025-06-05 | 2025-08-01 | 2025-09-10 | Units will be arranged for delivery by this week. Awaiting RTA inspection (expected by tommorow) |  |  |  | Qty: 1 Each 1. Aluminium Scoop Stretcher 2. LIFEPAK 1000 Defibrillator 3. ACCUVAC Lite Suction 4. Laryngoscope Handle (blades 0–5) |  | AUG: 11 |  | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 448800 | 7480000 | In Progress ¦ Missing Material ¦ APPLIED
41 |  |  | 5829 | 1910 | 102978 | Cluster2 | Type II ambulances | 9 | Semi-Gov. | In Progress | Dubai/JED | 2025-12-16 | Qadomi : Nov - 2025 | 2025-10-10 | 9 kits delivered | All chassis received. Awaiting pending Kits from Dubai - Received Partial materials on 25/06/2025. Remaining ETA- 15/07/2025-Still not received. |  | 9 In JED | Qty: 9 Each 1. Medsource Extrication Device 2. Aluminium Scoop Stretcher 3. Head Immobilizer Set 4. Adjustable Cervical Collar 5. Pediatric Immobilization Board 6. Spider Straps 7. Traction Splint Kit 8. Flex‑All Splint 9. Deluxe Spine Board 10. Child Traction Splint Kit 11. Power Load Cot Fastener 12. POWER‑PRO XT Cot 13. Chest Compression Machine 14. LIFEPAK 15 Defibrillator 15. LIFEPAK CR2 Defibrillator Qty: 18 16. Oxygen Regulator Flow |  | DEC: 9 |  | Up to a maximum of 20%. | CRITICAL |  | 8997750 | In Progress ¦ Missing Material ¦ CRITICAL
42 | Duha | 2024 | 5185 | 1814 | 102792 | Saudi Air forces | Fire truck - MAN 4x2 | 5 | Gov. | In Progress | Dubai | 2026-06-24 | 2025-09-01 |  | units expected to be ready for delivery on SEP | [5 empty] | SEP: 5 |  | Up to a maximum of 6%. | SAFE | 0 | 10177500 | In Progress ¦ No Missing ¦ SAFE
43 |  |  |  | 1815 |  |  | Aerial basket IVECO | 3 |  | In Progress | Dubai |  | 2026-06-24 |  | This subcontractor is working in KSA with Palfinger. According to the supplier, the unit will be ready in one week, and they are requesting payment. Our purchasing team has already informed the KSA purchasing team to process the payment. | [17 empty] | 3 |  |  | 0 | 2566800 | In Progress ¦ No Missing ¦
44 | Rahaf | NEW | 6052 | 1938 | 103055 | Al-Jazerah / john hopkins aramco | Type I ambulances | 20 | Private | In Progress | Dubai/JED | Prototype, 1-May-2025 2 Units, 28-Jun-2025 3 Units, 28-Jul-2025 4 Units, 28Aug-2025 5 Units, 28-Sep-2025 5 Units, 28-Oct-2025 | Qadomi: June: 1 unit – immediate delivery upon receipt. July: 2 boxes – 2–3 weeks after receipt (ETA 14 August). August: 5 boxes – 2–3 weeks after receipt (ETA 11 September). September: 7 boxes – 3–4 weeks after receipt (ETA 5 October). Note: Raw material processing requires 1–2 months for full fabrication and assembly of the boxes. |  | 1 unit is ready for delivery with pending materials 2 boxes under process to be finished on This month 5 units row materials are ready for shipping | 1 unit In Progress Qadomi: June: 1 unit – immediate delivery upon receipt. July: 2 boxes – 2–3 weeks after receipt (ETA 14 August). August: 5 boxes – 2–3 weeks after receipt (ETA 11 September). September: 7 boxes – 3–4 weeks after receipt (ETA 5 October). Note: Raw material processing requires 1–2 months for full fabrication and assembly of the boxes. | Based on Luay Update on 22/6: 1 unit will be delivered this month 2 boxes in July 5 boxes in August 7 boxes in September |  |  | Prototype, 1-May-2025 2 Units, 28-Jun-2025 3 Units, 28-Jul-2025 4 Units, 28Aug-2025 5 Units, 28-Sep-2025 5 Units, 28-Oct-2025 | JUL: 1; AUG: 2; SEP: 5; OCT: 12 |  | 0.5% deduction for each late week, up to a maximum of 6%. | CRITICAL | 0 | 9700000 | In Progress ¦ No Missing ¦ CRITICAL
45 | Obada | NEW | 6238 |  | 103060 | JEDCO | Type II ambulances | 2 | Semi-Gov. | In Progress | Dubai | 2025-10-30 | 2025-10-01 |  | under process. Units will be ready by Oct 2025 | [5 empty] | OCT: 2 |  | 1% deduction for each late week, up to a maximum of 6%. | CRITICAL | 0 | 1087000 | In Progress ¦ No Missing ¦ CRITICAL | NO Palinty
46 |  |  | Al Jeel PO#5835 | 1664 | 103056 | KFSH | Medical Item | 3 | Semi-Gov. | Pending | Purchase | 2025-02-23 | 2025-10-01 | 2025-10-10 |  |  |  |  | Qty: 3 1. Chest Compression Machine |  | OCT: 3 Items |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 249000 | Pending ¦ Missing Material ¦ APPLIED
47 |  | 2024 | 5765 |  | 102962 | IHCC-JEDDAH | Ambulance | 1 | Private | In Progress | Dubai/JED | 2025-04-13 | [21 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 37320 | 622000 | In Progress ¦ No Missing ¦ APPLIED | NO Palinty | bar: JAN to DEC
48 |  |  | 5628 | 1878 | 102924 | Redsea Terminal | Ambulance | 1 | Semi-Gov. | Completed | Dubai | 2025-03-05 | 2025-07-20 |  | Delivered | [18 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 26910 | 448500 | Completed ¦ No Missing ¦ APPLIED | NO Palinty | bar: JAN to DEC
49 |  |  | 4949 | 1898 | 102711 | SGH-MEAHCO | Ambulance | 1 | Private | In Progress | Dubai/JED | 2025-10-07 | Waiting ETA from Dubai |  | Units is ready just awaiting the side and rear glass to deliver the unit. ETA for the glass next week | [18 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 33300 | 555000 | In Progress ¦ No Missing ¦ APPLIED | NO Palinty | bar: JAN to DEC
50 |  |  | 4319 | 1658 | 102441 | MBL(Dairiah Farm) | RIV | 1 | Private | In Progress | Dubai | 2024-08-04 | 2025-08-25 |  | Awaiting chassis. Unit suppose to be ready end of AUG |  |  |  |  | 2024-08-04 | [13 empty] | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 80506.44 | 1341774 | In Progress ¦ No Missing ¦ APPLIED | NO Palinty | bar: JAN to DEC
51 |  |  | 4609 |  | 102597 | Acwa Power | F.F truck | 1 | Private | Completed | Dubai | 2024-12-31 | Delivered |  |  |  | Delivered |  |  | 2024-12-31 | [13 empty] | 1% deduction for each late week, up to a maximum of 6%. | SAFE | 0 | 1867278 | Completed ¦ No Missing ¦ SAFE | bar: JAN to DEC
52 |  |  | Al Jeel PO#5835 |  | 102898 | KFSH | Medical Item | 1 | Semi-Gov. | Pending | Purchase | 2024-12-22 | 2025-10-10 | 2025-10-10 |  |  |  |  | Qty: 1 1. Chest Compression Machine | 2024-12-22 | OCT: 1 Item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 83000 | Pending ¦ Missing Material ¦ APPLIED
53 | Khaled | NEW | Zimmo PO#6673 reversed to Aljeel | 2114 | 103134 / 103156 | Security Forces Hospital | Medical Item | 4 | Gov. | Pending | Purchase | 2025-08-28 |  | 2025-09-15 |  |  | Cancel the PO and revise the PR and revise PO |  | Qty: 2 Each 1. Stryker MX-PRO R3 Cot 2. Stryker POWER-PRO XT Cot 3. Power Load System (6390) |  | OCT: 4 Items |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 375750 | Pending ¦ Missing Material ¦ APPLIED
54 |  | 2024 | 5272 | 1851 | 102744 | KAMC | Ambulance | 3 | Gov. | In Progress | Dubai | 2025-03-19 | 2025-11-01 |  | Luay : NOV |  |  |  | Qty: 3 1. Oxygen Cylinder Steel CGA 540, 3000L (MS‑SCYL‑M) Qty: 3 2. Aluminium Scoop Stretcher (MS‑SCP123‑S) Qty: 9 3. Adjustable Cervical Collar (MS‑92500) Qty: 3 4. Pediatric Immobilization Board (MS‑PIB‑1) Qty: 9 5. Flex‑All Splint (MS‑SPLINT) Qty: 3 6. Land Mobile Excel GSM Extender (HEA2 router + antennas + 10 m cable) Qty: 5 7. Portable Ventilator, Model T1 Qty: 2 8. Additional 3‑Year Warranty (Portable Ventilator) | 2025-03-19 | NOV: 3 |  | 1% deduction for each late week, up to a maximum of 6%. | APPLIED | 251941.2 | 4199020 | In Progress ¦ Missing Material ¦ APPLIED
55 |  |  | Al Jeel PO#5835 |  | 102959 | King Salman Hospital -Taif | Medical Item | 1 | Gov. | Pending | Purchase | 2024-11-12 | 2025-10-01 | 2025-10-10 |  |  | Oct, in discussion to make it before August |  | Qty: 3 Each 1. LIFEPAK 1000 Defibrillator 2. Oxygen Regulator Flow Meter 3. Power Load System | 2024-11-12 | NOV: 1 item |  | Depending on NUPCO | APPLIED | Depending on NUPCO | 514000 | Pending ¦ Missing Material ¦ APPLIED
56 |  |  | 25268 |  | 102948 | ADFA Contracting Jazan | Firefighting Suits | 1 | Private | Completed | Dubai | 2025-04-01 | 2025-04-01 | [7 empty] | APR: Suits |  | 1% deduction for each late week, up to a maximum of 6%. | SAFE | - | 186661.1 | Completed ¦ No Missing ¦ SAFE
57 | Osama | NEW | 6318 Zimmo PO#6649 | 1932-1959 | 103123/103126/103127 | Almoosa Health | AMBULANCE VEHICLE TYPE II | 2 | Private | In Progress | JED | 2025-10-13 | 2025-10-20 | 2025-10-15 | 2 units ready for shipment |  | PO raised for the chassis and ETA for the chassis in October |  | Qty: 4 Each 1. Stryker MX-PRO R3 X-Frame Amb Cot. 2. Stair Chair 3. Spine Backboard 4. Scoop Stretcher |  | OCT: 2 |  | 1% deduction for each late week, up to a maximum of 6%. | CRITICAL | 0 | 904000 | In Progress ¦ Missing Material ¦ CRITICAL | NO Palinty
58 | [6 empty] | AMBULANCE VEHICLE TYPE II | 1 |  | In Progress |  | 2025-10-16 | 2025-10-20 |  |  |  | PO raised for the chassis and ETA for the chassis in October | [16 empty] | 1% deduction for each late week, up to a maximum of 6%. | CRITICAL | 27120 | 452000 | In Progress ¦ No Missing ¦ CRITICAL | NO Palinty | bar: JAN to DEC
59 | [6 empty] | AMBULANCE VEHICLE TYPE II | 1 |  | In Progress |  | 2025-10-16 | 2025-10-20 |  |  |  | PO raised for the chassis and ETA for the chassis in October | [16 empty] | 1% deduction for each late week, up to a maximum of 6%. | CRITICAL | 27120 | 452000 | In Progress ¦ No Missing ¦ CRITICAL | NO Palinty | bar: JAN to DEC
60 |  | 2024 | 4490 | 1699 | 102586 | KING FAHAD UNIVERSITY | AMBULANCE VEHICLE TYPE II | 1 | Gov. | In Progress | Dubai | 2025-01-28 | To be confirmed once we finish the shipping documentation |  | units is ready for shipping only pending some materials |  | Unit almost ready. SRCA approval received and we will start with documentation for shipping | [16 empty] | 1% deduction for each late week, up to a maximum of 6%. | Applied | 41700 | 695000 | In Progress ¦ No Missing ¦ Applied | bar: JAN to DEC
61 |  |  | 5786 | 1905 | 102640 | Imam Abdulrahman Al Faisal Hospital - Dhahran | Fire truck | 1 | Gov. | In Progress | Dubai | 2025-09-30 | 2025-12-01 |  | Unit will be arranged for delivery on Dec-25 |  | Chassis will be received on Oct |  | Qty: 4 Each 1. SCBA 2. Air Cylinder 3. HUD Receiver 4. FPS 7000 Mask | [14 empty] | 1% deduction for each late week, up to a maximum of 6%. | Critical |  | 1489250 | In Progress ¦ Missing Material ¦ Critical | bar: JAN to DEC
62 |  |  | 4459 | 1691 | 102584 | KING FAHD MILITRY MEDCIAL COMPLEX DHAHRAN | Fire truck | 1 | Gov. | In Progress | Dubai | 2024-08-11 | 2025-09-10 |  | The unit will be ready for FAT on 10 August 2025. If no FAT is required, we will ship the unit after 10 August 2025. |  | Chassis received |  |  | 2024-08-11 | [13 empty] | Up to a maximum of 6%. | Applied | 81903 | 1365050 | In Progress ¦ No Missing ¦ Applied | bar: JAN to DEC
63 | Dam (Soliman hassan) | 2024 | 4110 | 1602 | 102408 | Blood bank - Almadinah | Mobile blood donation unit | 2 | Private | In Progress | Dubai | 2024-02-19 | 2025-07-07 |  | 1st week of July will be ready for shipping |  | Based on Luay Update on 24/6: The units have been ready for a long time, but the client requested several revisions for the sign writing. The sign writing was approved last Friday, and we will ship the units once the signwriting is finished. |  |  | 2024-02-19 | JUL: 2 |  | 1% deduction for each late week, up to a maximum of 5%. | Applied | 75000 | 1500000 | In Progress ¦ No Missing ¦ Applied
64 |  |  | 4460 |  | 102578 | NESMA | 4x4 Ambulance | 4 | Private | Completed | Dubai | 2024-05-23 | Delivared | 2025-09-10 |  |  |  |  | Qty: 1 Oxygen Cylinder Steel CGA 540, 3000L Qty: 24 2. Ambulance Wall Bracket for LIFEPAK 1000 | 2024-05-23 | JAN: 1; FEB: 2; MAR: 1 |  | 1% deduction for each late week, up to a maximum of 6%. | SAFE | - | 1240000 | Completed ¦ Missing Material ¦ SAFE
65 |  |  |  | 1573 | 102320 | Al-Fanar | Type I Ambulance (NF-AMB-TI/GMC) | 4 | Private | Pending | Dubai | 2024-03-11 | last 2 in the RUH factory to be delivered, "insurance" |  |  |  | last 2 in the RUH factory to be delivered, "insurance" |  |  | 2024-03-11 | APR: 2; JUL: 2 |  | 1% deduction for each late week, up to a maximum of 6%. | SAFE | - | 4645100 | Pending ¦ No Missing ¦ SAFE
66 | EXPORT (Huthaifa & Mohamad) | NEW | 6191 |  | 103103 | Team one company for ambulance services | AMBULANCE VEHICLE TYPE II | 27 | Private | Pending | Dubai |  | 17 Units delivered, 10 in RUH Waiting 2nd payment |  | Delivered |  | 17 Units delivered, 10 in RUH Waiting 2nd payment |  |  |  | AUG: 10 |  | - | SAFE | - | 9179811 | Pending ¦ No Missing ¦ SAFE
67 |  |  | 6009 |  | 103022/102943 | Capital Ambulance For Medical services | AMBULANCE VEHICLE TYPE II | 20 | Private | Completed | Dubai |  | Delivared | 2025-07-20 | Delivered |  |  |  | Qty: 45 1. Hand Sanitizing Gel Dispenser with gel | [14 empty] | - | SAFE | - | 6821616 | Completed ¦ Missing Material ¦ SAFE
[16 empty] | Total number of projects | 67
[16 empty] | Total value including VAT | #REF!
[16 empty] | Total Ambulances | #VALUE!
[16 empty] | Total Fire Truck | #REF!
[16 empty] | Total Medical Items | 51
[16 empty] | Projects with delay penalties | #REF!
[16 empty] | Projects with Critical status | 9
[16 empty] | Projects with Safe status | #REF!
[16 empty] | Projects with missing items | #REF!
[16 empty] | Month | Scheduled deliveries
[16 empty] | Jan | #REF!
[16 empty] | Feb | 2
[16 empty] | Mar | 1
[16 empty] | Apr | 3
[16 empty] | May | #REF!
[16 empty] | Jun | #REF!
[16 empty] | Jul | #REF!
[16 empty] | Aug | #REF!
[16 empty] | Sep | #REF!
[16 empty] | Oct | #REF!
[16 empty] | Nov | #REF!
[16 empty] | Dec | #REF!
[16 empty] | 2026 | #REF!
[16 empty] | TOTAL | #REF!
Note on N42: Author: ETA from JED ¦ Awaiting Dubai to send the kits

## Invoicing plan 2026
No. | Done by | # | PO# | Proj. No | SO number | Customer | JOH | QTY | Total Value | Pending Value |  | Delivery based on the contract | Statues | Remarks | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TTL 2026 | 2027
1 | Nader | 2025 | 5929 | 1921 | 103009 | Afras - Custom project | Combined Fire & Rescue Vehicle | 3 | 6132000 | 0 | Dubai | 3 Units,12-Dec-2025 3 Units, 12-Feb-2026 3 Units, 13-Apr-2026 | Completed | Done | FEBRUARY: 6132000 | 6132000 | 0
2 |  |  |  | 1923 |  |  | Light Rescue Vehicle | 2 | 3160000 | 0 | Dubai | 3 Units,12-Dec-2025 3 Units, 12-Feb-2026 3 Units, 13-Apr-2026 | Completed | Done | FEBRUARY: 3160000 | 3160000 | 0
3 |  |  |  | 1924 |  |  | Water Tanker | 4 | 6501200 | 0 | Dubai | 5 Units,12-Dec-2025 5 Units, 12-Feb-2026 10Units, 13-Apr-2026 | Completed | Done | FEBRUARY: 6501200 | 6501200 | 0
4 |  |  |  | 1922 |  |  | Rapid Intervention Vehicle | 4 | 3520000 | 0 | Dubai | 3 Units,12-Dec-2025 3 Units, 12-Feb-2026 3 Units, 13-Apr-2026 | Completed | Done | FEBRUARY: 3520000 | 3520000 | 0
5 |  |  |  | 1920 |  |  | Hazmat Vehicle | 3 | 8982000 | 0 | Dubai | 2 Units,12-Dec-2025 3 Units, 12-Feb-2026 2 Units, 13-Apr-2026 | Completed | Done | FEBRUARY: 8982000 | 8982000 | 0
6 |  |  | 5818 | 1906 | 102964 | SRCA - Ambulances | Nupco - 57 ambulances | 0 | 605341 | 0 | KSA | 2026-06-17 | Completed | Done | MAY: 605341 | 605341 | 0
7 |  |  | 4083 | 1593 |  | SAR | FIRE FIGHTING & RESCUE VEHICLE | 15 | 38692500 | 38692500 | Dubai | 2024-09-19 | Delayed | 1st Fire Truck in Jed, Monitor Broken 4 Ready For FAT: 22 - 23Jun 10 under production, shakeel will share report | JULY: 2579500; AUGUST: 10318000; SEPTEMBER: 25795000 | 38692500 | 0
8 |  |  |  | 1589 |  |  | RailRoad Type I ambulance | 6 | 10569900 | 10569900 | Dubai |  | Delayed | Received in Jeddah, ready for delivery, still waiting SASO inspection | JULY: 5284950; AUGUST: 5284950 | 10569900 | 0
9 | [6 empty] | NFPA 1917 | 1 | 126500 | 126500 | Dubai |  |  |  | SEPTEMBER: 126500 | 126500 | 0
10 | [6 empty] | AMC-3 years ambulances | 1 | 1080000 | 1080000 | Dubai |  |  |  | SEPTEMBER: 1080000 | 1080000 | 0
11 | [6 empty] | AMC-3 years firetrucks | 1 | 4200000 | 4200000 | Dubai |  |  |  | SEPTEMBER: 4200000 | 4200000 | 0
12 | Mahmoud | 2025 | 7259 | PR#2554 Start Date 8/25/2025 | 103252/103251 | Afras | Hazmat Vehicle | 2 | 6785000 | 6785000 | KSA | No ETA | Pending | In Hold | [12 empty] | 0 | 6785000
13 |  |  |  | 2071 | 103351 ¦ 103243 | NUPCO-General Administration of Support | AMBULANCE TYPE II | 6 | 3216000 | 0 | KSA | 2026-04-01 | Completed | Done | MAY: 3216000 | 3216000 | 0
14 | [6 empty] | XFRAME STRETCH AMBU II MX PRO R3 STRYKER | 6 | 152500 | 0 | KSA |  | Completed | Done | MAY: 152500 | 152500 | 0
15 |  |  | 6151 | 1985 | 103084 | Royal air defense | water tanker (18,000 Ltrs) | 2 | 2787000 | 2787000 |  | 2026-01-28 | In Progress | Expected to move from Dubai on 15 July as per the latest update | AUGUST: 2787000 | 2787000 | 0
16 |  |  |  | 1984 |  |  | RIV F-550 | 3 | 4761900 | 4761900 |  | 2026-01-28 | In Progress | Expected to move from Dubai on 15 July as per the latest update | AUGUST: 4761900 | 4761900 | 0
17 |  |  |  | 2016 | 103165 | Royal air defense | AMBULANCE TYPE II | 1 | 633000 | 633000 | KSA | 2025-08-20 | In Progress | Ready for Delivery, Waiting Arkan to Deliver Materials | JUNE: 633000 | 633000 | 0
18 |  |  | 6052 | 1938 | 103055 | Al-Jazerah / john hopkins aramco | AMBULANCE | 19 | 9215000 | 9215000 | KSA | Prototype, 1-May-2025 2 Units, 28-Jun-2025 3 Units, 28-Jul-2025 4 Units, 28Aug-2025 5 Units, 28-Sep-2025 5 Units, 28-Oct-2025 | In Progress | 1st Amb, dispatched from AFS. 19 Units pending the boxes from Dubai + raw materiaks | JULY: 4850000; AUGUST: 4365000 | 9215000 | 0
19 |  |  | 4109 | 1605/1606 | 102412 | KFSHRC - RIYADH | Hazmat & Hazard | 2 | 2039069 | 2039069 |  | 2024-09-03 | In Progress | 1 Unit Pass SASO 1 Unit waiting SASO | JULY: 2039069 | 2039069 | 0
20 |  | 2026 | PO NUPCO 4600119387 WO # 26917177 PO#9090 | 2129 | 103453 | King Fahad Military Med. City | AMBULANCE TYPE II | 1 | 1111150 | 1111150 | KSA | 2027-02-04 | In Progress | Chassis PO is still pending from CEO's office. Waiting for raw materials from Dubai | [12 empty] | 0 | 1111150
21 |  |  |  | 2130 |  |  | AMBULANCE TYPE I | 1 | 866580 | 866580 | KSA | [15 empty] | 0 | 866580
22 |  |  | PO-085018 |  |  | AFRAS - SEAFTY | SEAFTY | 1 | 1009023.71 | 0 | KSA |  | Completed |  | MARCH: 1009023.71 | 1009023.71 | 0
23 |  |  | 9008 | 2135 | 103416 | DR. SULAIMAN AL HABIB | AMBULANCE TYPE II | 50 | 17137500 | 17137500 | KSA | 2027-06-05 | In Progress | Waiting for the chassis. Firs raw materials Batch received in JED. Second batch under process | AUGUST: 5141250; SEPTEMBER: 5141250; OCTOBER: 6855000 | 17137500 | 0
24 |  |  | New | WO# NIS27063349 | 103486 | RAC | Mobile Command Vehicle | 4 | 2289600 | 2289600 | KSA | 2027-04-02 | In Progress | Po sent to Dubai | [12 empty] | 0 | 2289600
25 | [6 empty] | Structural Pumpers | 3 | 6180000 | 6180000 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 6180000
26 | [6 empty] | Heayy Rescue Vehicle | 2 | 2880000 | 2880000 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 2880000
27 | [6 empty] | Light Rescue Vehicle | 2 | 3640000 | 3640000 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 3640000
28 | [6 empty] | Hazmat Vehicle | 1 | 1688000 | 1688000 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 1688000
29 | [6 empty] | AMBULANCE | 1 | 699036 | 699036 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 699036
30 | [6 empty] | Mini Pumper | 2 | 2100000 | 2100000 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 2100000
31 | [6 empty] | Water Tanker | 2 | 3400000 | 3400000 | KSA | 2027-04-02 | In Progress | [13 empty] | 0 | 3400000
32 |  |  | 4500845450 | WO# NIS27070253 | 103522 | MBCC | First response Vehicle | 1 | 690000 | 690000 | KSA | 2026-11-24 | In Progress | Po sent to Dubai | [12 empty] | 0 | 690000
33 | Abdullah | 2025 | 6342 / WO # 25616597 | 1847 / 1970 | 103074 | MOD | AMBULANCE TYPE II | 15 | 11584300 | 5058850 | KSA | 2025-11-20 | Delayed | 6 VEHICLES: Materials shipped from Dubai, completion Date expected next week | MAY: 6525450 | 6525450 | 5058850
34 |  |  | 6162 | 1952 | 103088 | SRCA | Electrical ambulance | 10 | 6000000 | 6000000 | Dubai | 2025-12-27 | Delayed | the units are expected to be received in KSA factory by the next week ,Tariq Said. | JULY: 6000000 | 6000000 | 0
35 |  |  | Dubai |  | 103076 | Amal hospital - Tabouk | Medical Item | 1 | 38425 | 0 | KSA | 2025-06-05 | Completed |  | JANUARY: 38425 | 38425 | 0
36 |  |  | 5185 | 1814 | 102792 | Saudi Air forces | Fire truck - MAN 4x2 | 2 | 3540000 | 0 | KSA | 2026-06-24 | Completed |  | JANUARY: 3540000 | 3540000 | 0
37 |  |  | 4906 | 1791 | 102699 | King Faisal Specialist Hospital | AMBULANCE TYPE I | 1 | 652900 | 0 | KSA | 2025-04-30 | Completed |  | APRIL: 652900 | 652900 | 0
38 |  |  | 5829 | 1910 | 102978 | Cluster2 | AMBULANCE TYPE II | 9 | 8997750 | 0 | KSA | 2025-12-16 | Completed |  | JANUARY: 999750; MARCH: 7998000 | 8997750 | 0
39 |  |  | Al Jeel Medical PO#5727 |  | 102934 | Nupco - Riyadh - مدينة الملك عبدالعزيز | Supply of Medical Items | 1 | 25500 | 25500 | KSA |  | Delayed | Not received yet from Al jeel | JULY: 25500 | 25500 | 0
40 |  |  | Al Jeel Medical PO#5835 |  | 102958 | Nupco - Jizan - Jizan University | Supply of Medical Items | 1 | 163750 | 0 | KSA | 2025-05-01 | Completed |  | MARCH: 163750 | 163750 | 0
41 |  |  | 76835 CPO | 1464 | 102975 | KFSH | Supply of Medical Items | 1 | 162000 | 0 | KSA |  | Completed |  | JANUARY: 162000 | 162000 | 0
42 |  | 2026 |  |  | 103479 | NADEC | Water Tanker | 1 | 1500000 | 1500000 | KSA | 2027-02-10 | In Progress | Waiting for the Payment | [12 empty] | 0 | 1500000
43 | Abdulhamid | 2025 | Al Jeel Medical PO#6551 |  | 103156 | Security Forces Hospital | Medical Item | 4 | 375750 | 375750 | KSA | 2025-08-28 | In Progress | Ready for Delivery, needs to be discussed | JULY: 375750 | 375750 | 0
44 |  |  | Al Jeel Medical PO#6315 |  | 103111 | SRCA | Medical Item | 1 | 963500 | 963500 | KSA | 2025-07-14 | In Progress | Ready for Delivery, needs to be discussed | JULY: 963500 | 963500 | 0
45 |  | 2026 | PO NUPCO 4600119387 |  | 103421 | NUPCO - QASSIM ARMED FORCES HOSPITAL | Medical Item 1 Unit | 1 | 92800 | 92800 | KSA | 2025-05-21 | In Progress | Not received yet | JULY: 92800 | 92800 | 0
46 |  |  | Contract: ATT96412 |  | 103445 | NUPCO - MOD Saud Force | Medical Item 650 x 3 Units | 1 | 600500 | 600500 | KSA | 2026-04-27 | In Progress | Not received yet | [12 empty] | 0 | 600500
47 |  |  | 77175 |  | 103520 | KFSH | Medical Item | 1 | 83000 | 0 | KSA | 2026-04-28 | In Progress | AFS to delivery it | JUNE: 83000 | 83000 | 0
48 | ESSAM | 2026 | 1955 | WO# NIS27063313 | 103519 | Ministry of Defense | Fire Fighting Truck | 1 | 1500000 | 1500000 | KSA | 2026-05-19 | In Progress | POs for some materials sent to Dubai | NOVEMBER: 1500000 | 1500000 | 0
49 | Obada | 2025 | 6238 | 1964 | 103060 | JEDCO | AMBULANCE TYPE II | 2 | 1087000 | 0 | Dubai | 2025-10-30 | Delayed |  | APRIL: 1087000 | 1087000 | 0
50 |  |  | Al Jeel Medical PO#5835 |  | 103056 | KFSH | Medical Item | 3 | 249000 | 0 | KSA | 2025-02-23 | Completed |  | JANUARY: 249000 | 249000 | 0
51 |  |  | LOCAL |  | 102898 | KFSH | Medical Item | 1 | 83000 | 0 | KSA | 2024-12-22 | Completed |  | JANUARY: 83000 | 83000 | 0
52 |  |  | 5272 | 1851 | 102744 | KAMC | Ambulance | 3 | 4199020 | 0 | Dubai | 2025-03-19 | Delayed |  | APRIL: 1958700; MAY: 2240320 | 4199020 | 0
53 | Ahmed Qadomi | 2026 | NUPCO# 4600140435 PN#2157 PO#9426 | PO#9426 | 103482 | King AbdelAziz Med.City | AMBULANCE VEHICLE 4X4 | 4 | 3155150 | 3155150 | Dubai | 2026-09-27 | In Progress | Waiting for Chassis Qut from Purchase. Offline work on boxes is in progress | OCTOBER: 3155150 | 3155150 | 0
54 | Hatem | 2025 | 6318 | 1969-2044 | 103123 | Almoosa Health | AMBULANCE TYPE II | 2 | 904000 | 0 | KSA | 2025-10-13 | Completed | Done | FEBRUARY: 904000 | 904000 | 0
55 |  |  |  |  | 103126 |  | AMBULANCE TYPE II | 1 | 452000 | 0 | KSA | 2025-10-16 | Completed | Done | MARCH: 452000 | 452000 | 0
56 |  |  |  |  | 103127 |  | AMBULANCE TYPE II | 1 | 452000 | 0 | KSA | 2025-10-16 | Completed | Done | MARCH: 452000 | 452000 | 0
57 |  |  | 5786 | 1905 | 102640 | Imam Abdulrahman Al Faisal Hospital - Dhahran | Fire truck | 1 | 1295000 | 0 | Dubai | 2025-09-30 | Delayed | SASO | JUNE: 1295000 | 1295000 | 0
58 | Suliman | 2026 | 9108 | 2138 | 103469 | DACO | AMBULANCE TYPE II | 5 | 4541000 | 4541000 | Dubai | 2025-09-15 | In Progress | Waiting NEG POs for medicals. AL Jazerra to hold the 2 pickup chassis as per tariq request. Production going well so far, as per tariq | SEPTEMBER: 4541000 | 4541000 | 0
[7 empty] | Ambulance Vehicle - heavy duty Box Type | 1 | 873400 | 873400 | Dubai | 2025-09-15 | In Progress |  | SEPTEMBER: 873400 | 873400 | 0
|  |  |  | 2139 |  |  | Command/Rapid Response Vehicle | 3 | 1511100 | 1511100 | Dubai | 2025-09-15 | In Progress |  | SEPTEMBER: 1511100 | 1511100 | 0
[7 empty] | Pickup vehicle | 2 | 783300 | 783300 | Dubai | 2025-09-15 | In Progress |  | SEPTEMBER: 783300 | 783300 | 0
[7 empty] | Services Charge | 1 | 191200 | 191200 | Dubai | 2025-09-15 | In Progress |  | SEPTEMBER: 191200 | 191200 | 0
59 | Nadeem | 2026 | PO#4500664526 PR#4448 to make Full PO |  | 103534 | SE Company | INCIDENT COMMAND TRUCK (37116) | 15 | 14940675 | 14940675 | KSA | 2027-08-23 | In Progress | [13 empty] | 0 | 14940675
TOTAL | [7 empty] | 248 | 227846819.71 | 165684460 |  | Completed: 20 Pending: 1 In Progress: 30 |  | 0 | 5072175 | 29199200 | 10074773.71 | 3698600 | 12739611 | 2011000 | 22211069 | 32658100 | 36342750 | 10010150 | 1500000 | 0 | 173417428.71 | 54429391
[9 empty] | Total | Total Pending |  | Invoiced Up To Today | 62162359.71 |  | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TTL 2026 | 2027
[9 empty] | 227846819.71 | 165684460 |  |  |  |  | 5072175 | 29199200 | 10074773.71 | 3698600 | 12739611 | 2011000 | 22211069 | 32658100 | 36342750 | 10010150 | 1500000 | 0 | 173417428.71 | 54429391
[15 empty] | JULY: Invoicing |  |  | 2026 - Invoicing
[15 empty] | JULY: Jan - May (Achieved); SEPTEMBER: 62162359.71 |  |  | Done by | Target | Invoicing up to date | 2026 plan | Expeted Total invoicing 26 | % | Actual % up to now | Invoicing Carry Over 2027
[29 empty] | Nader | 60000000 | 28900541 | 54668900 | 83569441 | 139.3% | 48.17% | 0 | bar: JULY to AUGUST
[29 empty] | Zohairy | 25000000 | 4377523.71 | 36573469 | 40950992.71 | 163.8% | 17.51% | 32329366 | bar: JULY to AUGUST
[15 empty] | JULY: Plan up to End of 2026; SEPTEMBER: 111255069 |  |  | Abdullah | 25000000 | 20080275 | 6025500 | 26105775 | 104.4% | 80.32% | 6558850
[29 empty] | Essam | 2500000 | 0 | 1500000 | 1500000 | 60% | 0% | 0 | bar: JULY to AUGUST
[29 empty] | Abdulhamid | 1500000 | 83000 | 1432050 | 1515050 | 101% | 5.533% | 600500 | bar: JULY to AUGUST
[29 empty] | Obada | 5000000 | 5618020 | 0 | 5618020 | 112.4% | 112.4% | 0
[15 empty] | JUNE: Sales Men Wise; JULY: Invoicing up to date; AUGUST: %; SEPTEMBER: SO up to date; OCTOBER: % |  |  | Hatem | 5000000 | 3103000 | 0 | 3103000 | 62.06% | 62.06% | 0
[15 empty] | JUNE: Nader; JULY: 28900541; AUGUST: 139.3%; SEPTEMBER: 0; OCTOBER: 0% |  |  | Ahmed Qadomi | 2500000 | 0 | 3155150 | 3155150 | 126.2% | 0% | 0
[15 empty] | JUNE: Zohairy; JULY: 4377523.71; AUGUST: 163.8%; SEPTEMBER: 43690889.71; OCTOBER: 96.34% |  |  | Suliman | 0 | 0 | 7900000 | 7900000 | #DIV/0! | #DIV/0! | 0
[15 empty] | JUNE: Abdulla; JULY: 20080275; AUGUST: 104.4%; SEPTEMBER: 1500000; OCTOBER: 4.243% |  |  | Nadeem |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 14940675
[15 empty] | JUNE: Essam; JULY: 0; AUGUST: 60%; SEPTEMBER: 1500000; OCTOBER: 7.371% |  |  | NEW Salesman ( Riyadh) | 3500000 |  |  |  | 0% | 0%
[15 empty] | JUNE: Abdulhamid; JULY: 0; AUGUST: 101%; SEPTEMBER: 776300; OCTOBER: 31.05% |  |  | NEW Salesman ( Riyadh) | 2500000 |  |  |  | 0% | 0%
[15 empty] | JUNE: Obada; JULY: 5618020; AUGUST: 112.4%; SEPTEMBER: 0; OCTOBER: 0% |  |  | NEW Salesman ( Dammam ) | 2500000 |  |  |  | 0% | 0%
[15 empty] | JUNE: Hatem; JULY: 1808000; AUGUST: 62.06%; SEPTEMBER: 0; OCTOBER: 0% |  |  | Maintenance Dept.
[15 empty] | JUNE: Ahmed Qadomi; JULY: 0; AUGUST: 126.2%; SEPTEMBER: 3155150; OCTOBER: 31.55% |  |  | Baqir | 3000000 |  |  |  | 0% | 0%
[15 empty] | JUNE: Suliman; JULY: 0; AUGUST: #DIV/0!; SEPTEMBER: 7900000; OCTOBER: #VALUE! |  |  | Asad | 1500000 |  |  |  | 0% | 0%
[15 empty] | JUNE: Nadeem; JULY: 0; AUGUST: #DIV/0!; SEPTEMBER: 14940675; OCTOBER: #VALUE! |  |  | Muhannad | 1500000 |  |  |  | 0% | 0%
[15 empty] | JUNE: Tortal; JULY: 60784359.71; SEPTEMBER: 73463014.71 |  |  | ASD Dept.
[29 empty] | Hafiz | 1000000 |  |  |  | 0% | 0%
[29 empty] | Omar | 1000000 |  |  |  | 0% | 0%
[28 empty] | Invoicing target | Ossama | 1000000 |  |  |  | 0% | 0%
[28 empty] | 144000000 | Dept. | 144000000 | 62162359.71 | 111255069 | 173417428.71 | 120.4% | 43.17% | 54429391
SO target
[28 empty] | 245000000 | 2026 - SO
[29 empty] | Done by | Target (SO) | Achieved | 2026 plan | Total Ex. SO 26 | %
[29 empty] | Nader | 75350000 |  |  | 0 | 0%
[29 empty] | Zohairy | 45350000 | 43690889.71 |  | 43690889.71 | 96.34%
[29 empty] | Abdulla | 35350000 | 1500000 |  | 1500000 | 4.243%
[29 empty] | Essam | 20350000 | 1500000 |  | 1500000 | 7.371%
[29 empty] | Abdulhamid | 2500000 | 776300 |  | 776300 | 31.05%
[29 empty] | Obada | 10000000 |  |  | 0 | 0%
[29 empty] | Hatem | 7000000 |  |  | 0 | 0%
[29 empty] | Ahmed Qadomi | 10000000 | 3155150 |  | 3155150 | 31.55%
[29 empty] | Suliman | - | 7900000 |  | 7900000 | #VALUE!
[29 empty] | Nadeem | - | 14940675 |  | 14940675 | #VALUE!
[29 empty] | NEW Salesman ( Riyadh) | 10000000
[29 empty] | NEW Salesman ( Riyadh) | 10000000
[29 empty] | NEW Salesman ( Dammam ) | 5000000
Maintenance Dept.
[29 empty] | Baqir | 8000000 |  |  |  | 0%
[29 empty] | Asad | 2200000 |  |  |  | 0%
[29 empty] | Muhannad | 2200000 |  |  |  | 0%
ASD Dept.
[29 empty] | Hafiz | 1400000 |  |  |  | 0%
[29 empty] | Omar | 1400000 |  |  |  | 0%
[29 empty] | Ossama | 1400000 |  |  |  | 0%
[29 empty] | Dept. | 247500000 | 73463014.71 | 0 | 73463014.71 | 29.68%
[29 empty] | 2026 - SO | Ambulances | Fire Trucks
[29 empty] | 73271814.71 | 30169139.71 | 43102675
Note on O42: Author: Still Not invoicied in the sysyerm only MDN
Note on P42: Author: Still Not invoicied in the sysyerm only MDN
Note on O51: Author: Still Not invoicied in the sysyerm only MDN
Note on P51: Author: Still Not invoicied in the sysyerm only MDN